## KCRHA next 4 Quarters SEP CEO
UNAPPROVED DRAFT TIMELINE KEY ACTIONS TO CREATE AND INITIATE THE KING COUNTY REGIONAL HOMELESSNESS AUTHORITY (KCRHA)
Version 2.A SEP CEO Hire | Phase III: ILA Effective to Implementation Board Seated |  |  |  | Phase IV: IB Seated to CEO Hired | [5 empty] | Phase V: CEO Hired to KCRHA Initially Operational | [5 empty] | Phase VI: KCRHA Initially Operational to KCRHA Fully Operational (Est. December 2021)
as of 8.14.2020 | Q2 2020 |  |  |  | Q3 2020 | [5 empty] | Q4 2020 | [5 empty] | Q1 2021
| May |  | June |  | July |  | August |  | September |  | October |  | November |  | December |  | January |  | February |  | March
GC Governing Committee |  | 1st MTG 5.1 |  | MTG 6.18 | Special MTG 7.9 | MTG 7.16 |  | MTG 8.20 |  | Joint MTG GC/IB: CEO Hiring Process & Equity Session 9.17 |  | MTG 10.15 |  | MTG 11.19 |  | MTG 12.17 | [5 empty] | Quarterly MTG
|  |  | IB Nominating Committee |  |  | GC Seats the IB |  | IB Fully Seated
IB Implementation Board | [6 empty] | 1st MTG | Proposed MTG | Proposed MTG |  | Proposed MTG |  | Proposed MTG |  | Proposed MTG |  | Proposed MTG |  | Proposed MTG |  | Proposed MTG
AC Advisory Committee | [8 empty] | CoC Board as A.C. |  |  | Proposed AC MTG |  | Proposed AC MTG |  |  |  | Proposed AC MTG |  | Proposed AC MTG |  | Proposed AC MTG
CEO Chief Executive Officer | [5 empty] | CEO Recruiting Firm Hire & Recruitment |  |  |  | Hire CEO |  |  | CEO Submits 60-Day Staffing Plan
CEO May Hire Pre-Authorized Core Leadership Positions
KCRHA Organizational Stand Up Milestones | [9 empty] | KCRHA Assumes Regional Continuum of Care Lead Agency Functions (Assumes Delegation of CoC Lead Agency Function by the CoC Board) | [6 empty] | KCRHA Initially Operational & Initial Work Plan Due |  | CEA Team Transition Window
[10 empty] | KCRHA Establishes Initial Support Systems for HR, Legal, Fiscal, & IT | [6 empty] | Phase I Program Migration
[12 empty] | CEO Orientation |  |  |  |  | Establish Initial Contracting Team
This timeline provides an overview of actions that the King County Regional Homelessness Authority (KCRHA) and its bodies will take. It does not depict the substantial body of work that King County and Seattle will undertake to prepare for KCRHA and to transition funding, resources, and crisis reponse system leadership to the KCRHA.
Today

## KCRHA next 4 Quarters OCT CEO
DRAFT TIMELINE KEY ACTIONS TO CREATE AND INITIATE THE KING COUNTY REGIONAL HOMELESSNESS AUTHORITY (KCRHA)
Version 2.C JAN CEO Hire | Phase III: ILA Effective to Implementation Board Seated |  |  |  | Phase IV: IB Seated | [5 empty] | Phase V: KCRHA Financial Infrastructure Decided , AC Appointed, and CEO Vetting |  |  |  |  | Phase VI: CEO Hired to KCRHA Beginning Operations (Est. Feb-Mar 2021) | [5 empty] | Phase VII: KCRHA Initially Operational (Est. April 2021) |  |  |  | Phase VIII: KCRHA Initially Operational to KCRHA Fully Operational
as of 11.3.2020 | Q2 2020 |  |  |  | Q3 2020 | [5 empty] | Q4 2020 |  |  |  |  | Q1 2021 | [5 empty] | Q2 2021 |  |  |  | Q3 2021
| May |  | June |  | July |  | August |  | September |  | October |  | November |  | December | January |  | February |  | March |  | April |  | May | June | July |  | August | Sept
GC Governing Committee |  | 1st MTG 5.21 |  | MTG 6.18 |  | MTG 7.16 |  | MTG 8.20 |  |  |  | Joint MTG GC/IB: CEO Hiring Process & Equity Session 10.15 |  | MTG 11.19 |  |  | MTG 1.21 |  | MTG 2.18 |  |  |  | MTG 4.15 |  |  |  | MTG 7.15
|  |  | IB Nominating Committee |  |  | GC Seats the IB |  | IB Fully Seated
IB Implementation Board | [6 empty] | 1st MTG 8-13 | 2020-08-24 | 2020-09-09 |  | 2020-10-14 |  | 2020-11-10 |  | 2020-12-09 | 2020-01-13 |  | 2020-02-10 |  | 2020-03-10 |  | 2020-04-14 |  | 2020-05-12 | 2020-06-09 | 2020-07-14 |  | 2020-08-11 | 2020-09-08
AC Advisory Committee | [10 empty] | 10/7 CoC Board Mtg | 10/21 CoC Board Mtg |  | 11/18 Vote CoC Board as A.C. (possible) |  |  | Proposed AC MTG |  | Proposed AC MTG |  | Proposed AC MTG
CEO Chief Executive Officer | [5 empty] | CEO Recruiting Firm Hire & Recruitment | [11 empty] | Hire CEO | [5 empty] | CEO Submits 60-Day Staffing Plan
CEO May Hire Pre-Authorized Core Leadership Positions
KCRHA Organizational Stand Up Milestones | [19 empty] | KCRHA Initially Operational |  | CEA Team Transition Window
[10 empty] | Establish Initial Support Systems for HR, Legal, Fiscal, & IT | [11 empty] | Phase I Program Migration
KCRHA Assumes Regional Continuum of Care Lead Agency Functions (Assumes Delegation of CoC Lead Agency Function by the CoC Board)
[20 empty] | CEO Orientation |  |  |  | Establish Initial Contracting Team
This timeline provides an overview of actions that the King County Regional Homelessness Authority (KCRHA) and its bodies will take. It does not depict the substantial body of work that King County and Seattle will undertake to prepare for KCRHA and to transition funding, resources, and crisis reponse system leadership to the KCRHA. All future dates are subject to change.
Today