## Timelines & Deliverables
King County HMIS [DRAFT] Annual Work Plan 2026
|  | Status | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
|  |  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
System Administration and Project Management
System Administration
| Implement the HMIS and act as the liaison to the CoC. | Ongoing
| Maintaining current version of: interagency data sharing agreements, technical admin and security officer agreement and, Client consent forms, user code of ethics policy, HMIS policies and procedures. Monitoring for any updates needed throughout the year, informing KCRHA when updates are needed. | Ongoing
| Integrate the needs of new programs for data collection and reporting, and implement/training users on data entry and reporting protocols. | Ongoing
| Ensure all functionality and services provided by the HMIS are optimized. Ensure Users meet data collection standards. | Ongoing
| Maintain a list of agency administrators for the entire CoC. | Ongoing
| Coordination and maintenance of the Housing Inventory Chart. | Ongoing
Standards and Policy Coordination
| Manage agenda for and facilitate weekly HMIS/CE meetings/calls with HMIS Lead. | Weekly
| Participate regularly and actively in System Performance Steering Committee, Coordinated Entry Committee(as requested), or their successors. | Monthly | bar: January W2; February W2; March W2; April W2; May W2; June W2; July W2; August W2; September W2; October W2; November W2; December W2
| Ensure HMIS Standard Operating Policies and User Manual is maintained and updated as the CoC makes additions or changes to HMIS policy (by request) | Ongoing
| Ongoing monitoring of Users (user activity within the system) to ensure compliance with policies and procedures. | Ongoing
Reporting/Analysis/Data Management
Develop and Finalize Annual Data Quality Improvement Plan for following year | bar: December W1 to December W4
| Present quarterly system data quality report to HMIS Lead (includes overlapping enrollments) | Quarterly | bar: January W2 to January W3; April W2 to April W3; July W2 to July W3; October W2 to October W3
| Quarterly report out & narrative demonstrating status of all work plan responsibilities to the System Performance Committee | Quarterly | bar: January W2; April W2; July W2; October W2
| Report of Help desk tickets provided to System Performance Committee when they convene (types and resolutions) | Monthly | bar: January W2; February W2; March W2; April W2; May W2; June W2; July W2; August W2; September W2; October W2; November W2; December W2
| Assist/Submit Point in Time Count (PIT) - Unsheltered and Sheltered Count for 2026 | In Progress
| Assist/Submit Housing Inventory Count (HIC) | In Progress
HIC reporting per Dept of Commerce specifications | bar: July W1 to August W4
| Assist/Submit HUD System Performance Measures - FY24 | In Progress
Assist with HMIS Annual Performance Review (APR) | bar: June W1 to July W4
| Assist/Submit FY24 Longitudinal Systems Analysis (LSA) (Note: HUD final timeline TBD) | In Progress | bar: May W1 to December W4
Assist with CES APR content as needed | bar: January W1; October W1 to December W3
Assist with Annual CoC consolidated application to HUD as needed | bar: September W1 to September W4
Develop Annual system admin work plan for 2026, established with HMIS Lead | bar: October W4 to December W4
Initiatives, Technical Support, and Help Desk
Annual System-wide client record de-duplication
| Community Diversion Initiative: provide assistance ongoing TA/support to funders and agencies for tracking diversion-related data in HMIS. (Pending KCRHA policies and proceudres) | Ongoing
| Update Community Defined Outcome Metrics Sea/King Outcomes Report (keeping in mind the wellbeing blueprint) | Pending SPC invovlment | bar: July W1 to August W4
| Help desk assists Users with implementation of basic HMIS program setup; responds to helpdesk requests within 24 hours (48 hours average resolution) | Ongoing
| Maintain HMIS website | Ongoing
| Coordinated Entry related configurations are maintained | Ongoing
| Routine data management tasks, such as data cleansing, client merging, and data correction requests are completed within five business days or after approval by KCRHA | Ongoing
| Ongoing Support & Maintenance of Outreach Module (including training & managing of end-users) | Ongoing
| Ongoing Support & Maintenance of Inventory Module (including training & managing of end-users, specifically for Shelter Inventory) | Ongoing
Agency Management & Coordination
Annual user survey (implementation and summary) | bar: August W1 to December W4
| Quarterly meeting with Agency Leads/CE Trainers | Quarterly | bar: January W3; April W4; July W4; October W3
| New programs set-up and configured correctly within seven working days after approval by KCRHA | Ongoing
| Bi annual collection & review of Security Checklists | Biannual | bar: March W1 to April W4; September W1 to October W4
| Monthly emailed data quality reports are sent, and made available in Data Analysis tab | Monthly
| Review and Analysis of Data Integration Agencies workflow and data quality | Ongoing
Training/TA
Annual training calendar developed/approved | bar: December W1 to December W4
| New user trainings | Ongoing
| King County HMIS specific trainings per training calendar and ad hoc in collaboration with HMIS Lead/CEA | Ongoing
| Assist/support CE trainings or training materials as needed (Assessor/CE Tranier Refresher trainings) | Ongoing
| 100% of requested approved users will receive access to the HMIS within a two weeks of request & all required trainings are complete | Ongoing
| Agency newsletter - continuous improvement on content for ease of use | Monthly | bar: January W3; February W3; March W3; April W3; May W3; June W3; July W3; August W3; September W3; October W3; November W3; December W3
| On-site (as requested) agency TA/training sessions and remote 1:1 user support will continue remotely | Ongoing
| Report on utility & satisfaction of trainings (include post zoom meeting survey feedback in Quarterly System Report Out) | Quarterly | bar: January W1 to January W2; April W1 to April W2; July W1 to July W2; October W1 to October W2
| Review/update Clarity user manual | Biannual | bar: June W1 to June W4; December W1 to December W4
Annual Security Officer and Annual Privacy training (compliance process) | bar: September W1 to November W4
Review King County custom field picklist and make any adjustments (Language and AI/AN Tribal Designation etc.) | bar: August W2 to November W2
Coordinated Entry
| Configure New Programs, Screens, Inventory and assessments[ HTT, HNF, VBNL] (and update as requested) (custom development may require a separate SOW). | Ongoing
| Ensuring the HMIS is configured based on CE policies and procedures. Updating configuration upon request. | Ongoing
| Update HMIS User accounts per the documented CE workflow for CE Assessors | Ongoing
| Maintenaning list of CE Trainers | Ongoing
Annotations